## Sheet1
First stage
Duration in man hour
Test Plan
|  | Select Test Data |  |  |  | 8
|  | Test strategy |  |  |  | 4
|  | Objectives |  |  |  | 2
|  | Doc |  |  |  | 4
| Integration Plan |  |  |  |  | 4
System Integration
System call identification
|  |  | Lame |  |  | 4
|  |  | PGP |  |  | 4
System call removal
|  |  | Lame |  |  | 12
|  |  | PGP |  |  | 8
|  | I/O Module Design |  |  |  | 6
|  | I/O Module Implementation |  |  |  | 10
|  | Integration |  |  |  | 6
Test
|  | I/O Module Testing |  |  |  | 8
|  | System Testing |  |  |  | 16
|  | Necessary Changes |  |  |  | 8
|  | Doc |  |  |  | 4
Profile
|  | Process |  |  |  | 8 | Run concurrently with System Testing
|  | Doc |  |  |  | 3
Static analysis
|  | Compile for MIPS |  |  |  | 0.5
|  | Get Register usage |  |  |  | 1
|  | Get Instruction Frequency |  |  |  | 1
|  | Doc |  |  |  | 1
* slack time
Background
Research
|  |  | DLLs |  |  | 12
|  |  | MIPS Emulator in C |  |  | 24
|  |  | GNU Makefile |  |  | 12 | Run concurrent with DLLs
Practise
|  |  | Handel C |  |  | 200
|  |  | GCC / Cygwin |  |  | 40
Project Plan
|  |  | Work Breakdown |  |  | 6
|  |  | Time Allocation |  |  | 4
|  |  | Resource Allocation |  |  | 4
Progress Monitoring (Weekly)
|  |  | Review |  |  | 300
|  |  | Update |  |  | 90
[5 empty] | sub Total | 644
Second stage
General
Fixed point Migration
|  |  | Migration Plan |  |  | 8
|  |  | Implementation |  |  | 80
|  |  | Testing |  |  | 12
Custom Hardware
|  |  | Purchase |  |  | 0.5
|  |  | Build |  |  | 2
|  |  | Test |  |  | 2
|  |  | Write the driver |  |  | 6
Partitioning
|  | Produce Data Flow Graph of System |  |  |  | 60
|  | Select Candidate Hardware Functions |  |  |  | 4
FPGA/Host Interface design
|  |  | Control |  |  | 8
|  |  | Structure |  |  | 8
|  |  | Communication |  |  | 8
|  | System Architecture |  |  |  | 8
ASIP
Interface design
|  |  | Control |  |  | 8
|  |  | Structure |  |  | 8
|  |  | Communication |  |  | 8
|  | Change GCC backend |  |  |  | 20
|  |  | Test |  |  | 6
|  | Update MIPS Emulator |  |  |  | 4
|  |  | Test |  |  | 4
|  | Necessary Changes |  |  |  | 4
D3 compilation
|  | Edit |  |  |  | 12
|  | Proof Read |  |  |  | 28
| Stage Review |  |  |  |  | 7
to be finished by week 8 21 March
|  |  |  | Sub total |  | 315.5
Third stage
ASIP
|  | Port MIPS to Handel-C |  |  |  | 60
|  |  | Simulate |  |  | 20
|  |  | Add Parallelism |  |  | 30
|  |  | Optimise |  |  | 30
|  |  | Necessary Changes |  |  | 20
|  | Interface Implementation |  |  |  | 30
|  | Create EDIF version |  |  |  | 0.5
|  | System test |  |  |  | 40
Portitioning
|  | Porting to Handel -C |  |  |  | 120
|  |  | Simulate |  |  | 80
|  |  | Add Parallelism |  |  | 50
|  |  | Optimise |  |  | 40
|  |  | Necessary Changes |  |  | 80
|  | Interface Implementation |  |  |  | 30
|  | Module test |  |  |  | 6
|  | Create EDIF version |  |  |  | 10
|  | System test |  |  |  | 40
Review
|  |  |  | Sub total |  | 686.5
Fourth Stage
| Create DLLs |  |  |  |  | 10
| GUI |  |  |  |  | 2
| Integrate GUI and DLLs |  |  |  |  | 6
| System Test |  |  |  |  | 20
Documentation
|  | Edit |  |  |  | 60
|  | Proof Read |  |  |  | 30
Demonstration
|  | Plan |  |  |  | 6
|  | Practise |  |  |  | 10
|  | Execute |  |  |  | 1
Presentation
|  | Plan |  |  |  | 6
|  | Practise |  |  |  | 10
|  | Execute |  |  |  | 1
To be finished by week 16 |  |  |  |  | sub total | 162
[5 empty] | Total | 1808